Miyoungka (미영카) — Conversational English Program

Product Requirements Document

Author: Daniel Choi, Project Coordinator (Product & Growth)  •  Team: ISMP Korea  •  Status: Launched (Cohorts 1–2 complete)

Note on this document • This PRD is reconstructed from the real planning and results of the Miyoungka program for portfolio and interview-prep purposes. It's structured the way the original planning document would have been, with an added retrospective results section at the end.

# 1. Overview

Miyoungka (“American Café”) is a conversational English program built for Korean college students in Seoul. It pairs small groups of students with native English speakers for structured, informal conversation practice. This document lays out the plan for the initial pilot: the problem being solved, target users, go-to-market approach, success metrics, and phased cohort rollout.

# 2. Problem Statement

Korean college students have limited accessible, structured opportunities to practice conversational English with native speakers. Existing options are largely private academies (hagwons), which are expensive and formal, or informal language exchange meetups, which are inconsistent and unreliable. This leaves a gap in the market for an affordable, community-based, structured conversational program aimed specifically at college students.

# 3. Goals & Success Metrics

Primary goal: Validate demand and product-market fit for a paid, small-group conversational English program among Korean college students in Seoul.

## North Star metric

Cohort-over-cohort signup growth — the clearest signal of whether the program is building real pull rather than one-time interest.

## Supporting metrics

- Funnel conversion rate (Instagram click → paid signup)

- Session attendance rate, as a proxy for retention and satisfaction

- Profit per user, to validate the pricing and cost model

- Repeat / ambassador conversion rate, as a signal of genuine product-market fit

## Pre-launch targets (hypothesis)

- 20–30 signups for Cohort 1

- 5%+ end-to-end funnel conversion rate

- 40%+ session attendance rate

# 4. Target Users

Primary segment: Korean college students in Seoul, generally ages 18–28. Note: the ideal age range skews differently by gender than a typical U.S. college population, because male students' availability is affected by mandatory military service (roughly ages 20–28 for men vs. 18–25 for women).

Persona snapshot • “Min-jun,” 22, business major. Wants conversational fluency for internship interviews and study-abroad applications. Has tried language exchange apps but found them inconsistent and low-commitment. Price-sensitive but willing to pay for a structured, reliable experience.

# 5. User Journey

Instagram post/ad  →  Profile visit  →  Linktree  →  Landing page  →  Google Form signup  →  Payment  →  Onboarding (Notion hub)  →  First session

# 6. Requirements

## Must have

- Instagram presence with a consistent visual brand and posting cadence

- Linktree connecting Instagram traffic to the signup funnel

- Landing page explaining the program's value proposition and pricing

- Google Form + payment collection for signups

- Notion onboarding hub for enrolled students (schedule, materials, community)

## Should have

- A modest paid Instagram ad campaign targeting the core demographic

- A referral or “ambassador” mechanic to convert satisfied students into repeat participants

## Could have (future iterations)

- Automated reminders to improve session attendance

- Tiered pricing (e.g., group sessions vs. 1:1 conversation practice)

## Won't have (v1)

- A native mobile app

- An in-house learning management system

# 7. Go-to-Market Plan

| Channel | Approach |
| --- | --- |
| Organic Instagram | Mix of reels and static posts; reprioritize toward reels once early data shows which format performs better |
| Paid Instagram ads | Small always-on budget, iterating on targeting, creative, and messaging based on weekly performance |
| Campus outreach | Informal postering and flyering near target departments and dorms |
| Pricing | Set an initial price point, then adjust between cohorts based on conversion and attendance data |

# 8. Risks & Open Questions

- Unknown price sensitivity of the target segment going in — pricing may need to move after Cohort 1

- Unknown optimal session format and cadence for retention

- Military service timing constrains male student availability in ways that don't map to a typical Western college calendar

- Paid ad spend may not convert efficiently before the brand has any organic awareness or social proof

# 9. Cohort Rollout Plan

Cohort 1 (pilot, small and intentionally imperfect) → collect signal on messaging, pricing, and attendance → iterate → Cohort 2 (scale test) → evaluate full viability before committing to Cohort 3 and beyond.

# 10. Retrospective: Results After Cohorts 1–2

The section below reflects what actually happened once the program launched — included here to show the plan against the outcome.

| Metric | Result |
| --- | --- |
| Instagram growth | 0 → 1,200 followers in 4 months |
| Linktree performance | 1,405 views, 1,281 clicks (~91.2% CTR) |
| Cohort 1 signups | 31 |
| Cohort 2 signups | 63 (+103% vs. Cohort 1) |
| End-to-end funnel conversion | ~7.3% |
| Total users / paid users | 94 total, 73 paid |
| Paid conversion quality | Improved 74% → 79% through targeting and messaging optimization |
| Profit per user | ~$26 |
| Session attendance | ~50% of users attended 50%+ of sessions |
| Repeat users | 5 converted into Student Ambassadors |

# 11. Learnings & Next Steps

- Reels significantly outperformed static posts (roughly 750% higher engagement) — worth shifting content mix further in that direction for future cohorts

- Age and availability windows differ meaningfully by gender due to military service — segment outreach and messaging timing accordingly

- Small, iterative changes to pricing and messaging moved conversion measurably — build a lightweight, recurring test-and-learn cadence into every future cohort rather than treating launch as a one-time event